## Estimated Effort
Task Name | [8 empty] | Drew | Atticus | Benaiah | Will | Zach
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary) (secondary) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Preliminary & |  | Meetings and miscellaneous |  |  |  |  | 11.8 |  | 2.25 | 2.5 | 2.3 | 1.75 | 3
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 0
|  | Design architecture | Project Manager | Will | 12 |  | 0
| Requirements |  |  |  |  | 9 |  | 5
|  | Gather | Requirements Engineer | All | 2 |  | 2.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Analyze | Requirements Engineer | All | 4 |  | 2.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Specify | Requirements Engineer | All | 3 |  | 0
| Documentation |  |  |  |  | 19 |  | 26.35
|  | Project Charter | Project Manager | Will, Zach | 2 |  | 2.85 |  | 0.1 | 0.5 |  | 1 | 1.25
|  | Release Plan | Project Manager | Will | 2 |  | 0
|  | Requirements Document | Project Manager, Requirements Engineer | All | 5 |  | 10.5 |  | 3 | 2 | 1 | 1 | 3.5
|  | Project Plan | Project Manager, Developers | Will, All | 5 |  | 7.75 |  | 1.75 | 0.5 | 1.75 | 2.5 | 1.25
|  | Risk Management Report | Project Manager, Developers | Will, All | 3 |  | 3.5 |  | 1 |  | 2.25 |  | 0.25
|  | Architecture Document | Architect | Will, All | 2 |  | 1.75 |  |  |  | 1.75
|  | Test Report | Tester | TBD | TBD |  | 0
|  | User Guide and System Admin Doc | Developers, Requirements Engineer | TBD | TBD |  | 0
Iteration 1: | Design |  |  |  |  | 27 |  | 18
|  | Determine technology needs | Developers | All | 5 |  | 5 |  | 1 | 1 | 1 | 1 | 1
|  | Research and learn new language and environment | Developers | All | 20 |  | 11.5 |  | 2 | 2 | 2.5 | 2 | 3
|  | Initialize project and set up proxy server software | Production Engineer | Zach | 2 |  | 1.5 | [5 empty] | 1.5
| Analysis |  |  |  |  | 6 |  | 2.5
|  | System testing | Tester | Drew | 2 |  | 0
|  | Bug fix as required | Tester, Developer | All | 2 |  | 0
|  | Evaluate needs for next iteration | Project Manager | Will | 2 |  | 2.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Iteration 2: | Design |  |  |  |  | 5 |  | 6
|  | Site map | Project Manager | Will, Zach | 1 |  | 0
|  | Design prototype | UX Engineer | Atticus | 2 |  | 4.5 |  |  | 4.5
|  | Database design and schema | Database administrator | Zach, Benaiah | 2 |  | 1.5 | [5 empty] | 1.5
| Development |  |  |  |  | 14 |  | 8.75
|  | Create database and implement schema | Database administrator | Zach, Benaiah | 3 |  | 3.75 | [5 empty] | 3.75
|  | Page path URLs and page skeletons | Developers | Atticus | 2 |  | 0
|  | Non-functional login form | Developers | Benaiah | 1 |  | 2.5 |  |  |  | 2.5
|  | Mock transaction table | Developers | Will, Benaiah | 6 |  | 0
|  | Header and navigation menu | Developers | Drew | 2 |  | 2.5 |  | 2.5
| Analysis |  |  |  |  | 6 |  | 0.1
|  | System testing | Tester | Drew | 2 |  | 0.1 |  | 0.1
|  | Bug fix as required | Tester, Developers | Drew, All | 2 |  | 0
|  | Evaluate needs for next iteration | Project Manager | Will | 2 |  | 0
Iteration 3: | Design |  |  |  |  | 1 |  | 0
|  | Site map | Project Manager | Will, Zach | 1 |  | 0
| Development |  |  |  |  | 22 |  | 12.5
|  | Implement environment variables (user-secrets) | Database administrator | Zach | 1 |  | 1 | [5 empty] | 1
|  | Integrate database and create database tools | Database administrator | Zach, Benaiah | 6 |  | 4.5 | [5 empty] | 4.5
|  | Add ASP.NET Identity to project | Developers | Benaiah, Zach | 3 |  | 3.5 |  |  |  | 3.5
|  | Correct link to site URLs | Developers | Atticus | 2 |  | 0
|  | Add functionality to login form (dependency: Identity) | Developers | Benaiah, Zach | 2 |  | 0.75 |  |  |  | 0.5 |  | 0.25
|  | Integrate transaction table | Developers | Will, Benaiah | 6 |  | 0.25 | [5 empty] | 0.25
|  | Refactor existing structures as needed | Developers | All | 2 |  | 2.5 |  |  |  | 1 |  | 1.5
| Analysis |  |  |  |  | 6 |  | 0
|  | System testing | Tester | Drew | 2 |  | 0
|  | Bug fix as required | Tester, Developers | Drew, All | 2 |  | 0
|  | Evaluate needs for next iteration | Project Manager | Will | 2 |  | 0
Total |  |  |  |  | 127 | 127 | 91 | 91 | 15.2 | 14.5 | 21.55 | 10.75 | 29

## User Stories
ID | User Story Name | User Story Description | Priority | Estimated effort (hours) | Actual effort (if completed) | Status (completed, toDo, inProgress) | Developer names
1
2